## Gantt Chart
	Jawhm				11%
	Plate
	Khang		Wednesday, January 28, 2015

										05					06					07					08					09					10					11					12					13					14					15					16					17					18					19					20					21					22					23					24					25					26					27					28					29					30
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Jan-14					Feb-14					Mar-14					Apr-14					May-14					Jun-14					Jul-14
			27-Jan-2014	4	30-Jan-2014	11%	4			27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26
	テンプレートメール新規登録	Khang	27-Jan-2014	2	28-Jan-2014	25%	2	0	2
	テンプレートメール一覧
	Select from DB + show on layout		27-Jan-2014	0.5	27-Jan-2014	100%	1	0	1
	テンプレートメール登録
	Create form input		28-Jan-2014	0.5	28-Jan-2014		1	0	1
	Register new record and show on layout		28-Jan-2014	0.5	28-Jan-2014		1	0	1
	Edit form		28-Jan-2014	0.5	28-Jan-2014		1	0	1

	テンプレートメール（署名）新規登録	Khang	29-Jan-2014	1	29-Jan-2014	0%	1	0	1
	テンプレートメール（署名）一覧
	Select from DB + show on layout		29-Jan-2014	0.5	29-Jan-2014		1	0	1
	テンプレートメール（署名）登録
	Create form input		29-Jan-2014	0.5	29-Jan-2014
	Register new record and show on layout		29-Jan-2014	0.5	29-Jan-2014
	Edit form		29-Jan-2014	0.5	29-Jan-2014

	エベント登録・編集	Khang	30-Jan-2014	1	30-Jan-2014	0%	1	0	1
	Level 2 Task
	Level 3 Task		30-Jan-2014	1	30-Jan-2014		1	0	1

	Gantt Chart Template V1.1
	Author: Fernando Ribeiro <pinguim.ribeiro@gmail.com>

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays